## Sheet1
# | Title | Month | Feb | Feb | Feb | Feb/Mar | Mar | Mar | Mar | Mar/Apr | Apr | Apr | Apr | Apr/May | May | May | May | May | May/Jun | Jun | Jun
|  | Week | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Jonas & Lucas CT Bachelor Project
Analysis of Problem Domain
1 | Learn how VDM++ to UML works in Overture | bar: 6 to 7
2 | Understand current VDM++ in VS code extension | bar: 7 to 8
3 | Decide on implementation: Wrapper vs. LSP vs. VS code tools | bar: 8 to 9
Design
5 | Choose architecture | bar: 9 to 10
6 | Make overview of general design of the program | bar: 9 to 10
Implementation
7 | Develop first simple iteration (most likely using a wrapper) | bar: 11
8 | Development | bar: 12 to 17
9 | (Possibly) Add further functionality (real-time, bidirectional, etc.) | bar: 15 to 17
Thesis
10 | Chapter: Introduction | bar: 18
11 | Chapter: Background | bar: 6 to 10
12 | Chapter: Design | bar: 18 to 20
13 | Chapter: Implementation | bar: 20 to 21
14 | Chapter: Discussion | bar: 21 to 22
15 | Chapter: Conclusions and Future Work | bar: 22 to 23
16 | Chapter: Abstract | bar: 23 to 24
17 | Proof Reading | bar: 24
18 | Hand-in
= Milestone
: June 15
: Stop development